## 1. Function List
Infordio Web Form - Function List
No | Date | User Story | Priority | Status | Sprint | Note
1 | 2022-06-07 | Admin can create a Web Form from the Item Set | HIGH | DONE | Sprint 1
2 | 2022-06-07 | Admin can preview the Web Form and share a link to user | HIGH | DONE | Sprint 1
3 | 2022-06-07 | User can view the Web Form online (support mobile) | HIGH | DONE | Sprint 2
4 | 2022-06-07 | User can fill their answer to Web Form and submit it. | HIGH | DONE | Sprint 2
5 | 2022-06-07 | Admin can change theme for Web Form | LOW | DONE | Sprint 6
6 | 2022-06-07 | Admin can set passcode for Web Form | MEDIUM | DONE | Sprint 3
7 | 2022-06-07 | Admin can set expiration date for Web Form | LOW | DONE | Sprint 6
8 | 2022-06-07 | Admin can set an Item is mandatory or not | MEDIUM | DONE | Sprint 3
9 | 2022-06-13 | Admin can change the order of an item in the Web Form creation screen | LOW | DONE | Sprint 6
10 | 2022-06-13 | Different item sets between PDF Form and Web Form in case admin edit an item sets | LOW | DONE | Sprint 6
11 | 21/06/2022 | The other company can embedded Web Form into their product | LOW | DONE |  | Đã được đối ứng ở Task 12
12 | 28/06/2022 | Web Form should save as a static file (html/javascrip/css) in the server | HIGH | DONE | Sprint 4
13 | 2022-12-07 | Complete the current APIs | HIGH | DONE | Sprint 4
14 | 21/07/2022 | Admin can download static form 「確定」ボタンを押下後、「ダウンロード」ボタンを活性化させてダウンロードする仕様にしてください | HIGH | DONE | Sprint 4
| 2022-02-08 | The system can prevent multiple submissions from a browser. |  | DONE |  | Đã được đối ứng ở Task 12
15 | 16/08/2022 | Admin can set html file name khi ấn nút kakutei |  | DONE | Sprint 7 | Done
16 | 23/08/2022 | (Change Request) Admin vẫn có thể edit PDF Form sau khi ấn nút kakutei bên Web Form | HIGH | DONE | Sprint 6
17 | 2022-09-09 | Refactor form copy APIs |  | DONE | Sprint 8
18 | 2022-09-09 | Admin can import/export form data |  | DONE | Sprint 8
19 | 2022-09-20

## 2. Sprint Planning
Infordio Web Form - Sprint Planning
Sprint | User Story | Task | Days | Start Date | End Date | Status | Note
Sprint 0 |  |  |  | 2022-06-01 | 2020-06-07 | Done
| Preperation | Study the current system | 2 | 2022-06-01 | 2022-06-02 | Done
|  | Setup development enviroment | 2 | 2022-06-02 | 2022-06-03 | Done
|  | Function List & Sprint Planning | 1 | 2022-06-06 | 2022-06-08 | Done
Sprint 1 |  |  |  | 2022-06-09 | 2022-06-22 | Done
| Design | Specification | 7 | 2022-06-09 | 2022-06-17 | Done
|  | Database Design | 3 | 2022-06-10 | 2022-06-13 | Done
|  | Sequence Diagram | 4 | 2022-06-13 | 2022-06-17 | Done
|  | API Specification | 4 | 2022-06-13 | 2022-06-17 | Done
| 1. Admin can create a Web Form from the Item Set | [Back-end] Update database | 1 | 2022-06-13 | 2022-06-13 | Done
|  | [Back-end] Create APIs for Web Form | 5 | 2022-06-14 | 2022-06-14 | Done
|  | [Front-end] Create Item Set Components | 5 | 2022-06-09 | 2022-06-15 | Done
|  | [Front-end] Web Form Creation Page | 3 | 2022-06-16 | 2022-06-20 | Done
| 2. Admin can preview the Web Form and share a link to user |  |  |  |  | Done
|  | [Front-end] Create Web Form Preview Page | 1 | 2022-06-21 | 2022-06-21 | Done
|  | [Front-end] Web Form Link Dialog for Sharing | 1 | 2022-06-22 | 2022-06-22 | Done
Sprint 2 |  |  |  | 2022-06-23 | 2022-07-06 | Done
| 3. User can view the Web Form online (support mobile) | [Back-end] Update Database | 2 | 2022-06-23 | 2022-06-24 | Done
|  | [Back-end] Create APIs for display Web Form | 3 | 2022-06-27 | 2022-06-29 | Done
|  | [Front-end] Web Form: Generate and Display Web Form Page | 2 | 2022-06-23 | 2022-06-29 | Done
| 4. User can fill their answer to Web Form and submit its | [Back-end] Create APIs for save Web Form results | 2 | 2022-06-27 | 2022-06-28 | Done
|  | [Front-end] Save User Input | 4 | 2022-06-29 | 2022-07-01 | Done
| Bug fixing & Improvement | Bug fixing & Improvement | 3 | 2022-07-04 | 2022-07-06 | Done
Sprint 3 & 4 |  |  |  | 2022-07-07 | 2022-08-17 | Done
8. Admin can set an Item is mandatory or not
|  | [Front-end] Admin can set required/optional for an Item Set | 1 | 2022-07-08 | 2022-07-08 | Done
|  | [Front-end] Display and validate item set with required/optional | 1 | 2022-07-11 | 2022-07-29 | Done
6. Admin can set passcode for Web Form
|  | [Backend] API for passcode | 2 | 2022-07-08 | 2022-07-12 | Done
|  | [Front-end] Admin can set the passcode for Web Form | 1 | 2022-07-12 | 2022-07-12 | Done
|  | [Front-end] Display the passcode dialog & check if passcode match incase the Web Form required a passcode | 1 | 2022-07-13 | 2022-07-13 | Done
| 12. Web Form should save as a static file (html/javascrip/css) in server |  |  | 2022-07-13 | 2022-08-08 | Done
|  | Research & basic implemenation | 4 | 2022-07-13 | 2022-07-18 | Done
|  | UI Implementation & Javascript validation for Item Sets with 1 input field (5 Item Sets) | 2.5 | 2022-07-19 | 2022-07-20 | Done
|  | UI Implementation & Javascript validation for select box/dropdown Item Sets (6 item sets) | 3 | 2022-07-21 | 2022-07-25 | Done
|  | UI Implementation & Javascript validation for Item Sets with multiple input fields (8 Item Sets) | 3 | 2022-07-26 | 2022-07-28 | Done
|  | Upload static page to S3 | 1 | 2022-07-25 | 2022-07-28 | Done
|  | Delete static page in S3 | 0.5 | 2022-07-26 | 2022-07-28 | Done
|  | Đánh giá tính khả thi cho phương án dùng chung validation code giữa Vue.js Web Form và Static Web Form | 1 | 2022-07-28 | 2022-07-28 | Done
|  | Dùng chung validation code giữa Vue.js và static Web Form | 4 | 2022-08-03 | 2022-08-08 | Done
| 13. Complete the current APIs |  |  | 2022-07-13 | 2022-08-17 | Done
|  | Research and create a proposal improvement list | 4 | 2022-07-13 | 2022-07-27 | Done
|  | Authentication with AWS API Key | 2 | 2022-08-03 | 2022-08-04 | Done
|  | Verify with Web Form Token | 3 | 2022-08-05 | 2022-08-09 | Done
|  | Validate web form submitted data at backend | 4 | 2022-08-10 | 2022-08-16 | Done
|  | Create guideline for create API Gateway Key | 2 | 2022-08-10 | 2022-08-17 | Done
| 14. Admin can download static form 「確定」ボタンを押下後、「ダウンロード」ボタンを活性化させてダウンロードする仕様にしてください |  |  | 27/07/2022 | 2022-08-09 | Done
|  | API for download static page | 1.5 | 27/07/2022 | 2022-01-08 | Done
|  | Update UI | 0 | 28/07/2022 | 2022-01-08 | Done
|  | API for rename html file | 0.5 | 2022-08-09 | 2022-08-09 | Done
|  | UI for rename html file | 0.5 | 2022-08-09 | 2022-08-09 | Done
| 10. Different item sets between PDF Form and Web Form in case admin edit an item set |  |  |  |  | Done
|  | Implementation | 2 | 2022-08-18 | 2022-08-24 | Done
|  | Update validation logic | 1 | 2022-08-24 | 2022-08-24 | Done
9. Admin can change the order of an item in the Web Form creation screen
|  | Implementation | 3 | 2022-08-18 | 2022-08-22 | Done
|  | Testing & bug fixings | 1 | 2022-08-23 | 2022-08-23 | Done
7. Admin can set expiration date for Web Form
|  | Implement UI | 1.5 | 2022-08-22 | 2022-08-23 | Done
|  | Implement backend | 1.5 | 2022-08-22 | 2022-08-23 | Done
|  | Testing & bug fixings | 0.5 | 2022-08-24 | 2022-08-24 | Done
| 5. Admin can change theme for Web Form |  |  | 2022-08-25 | 2022-08-31 | Done
|  | Theme setting UI | 2 | 2022-08-25 | 2022-08-26 | Done
|  | Theme setting API | 2 | 2022-08-25 | 2022-08-26 | Done
|  | Theme setting integration | 3 | 2022-08-29 | 2022-08-09 | Done
|  | Theme setting for static page | 3 | 2022-08-29 | 2022-08-09 | Done
|  | Resize able logo image |  | 2022-09-05 | TBD | Done
| 15. Admin can set html file name khi ấn nút kakutei |  |  |  |  | Done
|  | API for S3 folder/file name |  | 2022-09-05 | 2022-09-06 | Done
|  | Update UI |  | 2022-09-05 | 2022-09-06 | Done
| 16. (Change Request) Admin vẫn có thể edit PDF Form sau khi ấn nút kakutei bên Web Form |  | 1 | 2022-08-24 | 2022-08-24 | Done
| Update Test Cases & Test Report |  |  | 2022-09-09 | 2022-09-15 | Done
17. Refactor form copy APIs
|  | Create & update sequence diagram | 2 | 2022-09-12 | 2022-09-15 | Done
|  | Code demo main flow | 2 | 2022-09-16 | 2022-09-19 | Done
|  | Refactor & implement all logic | 3 | 2022-09-20 | 2022-09-22 | Done
|  | Test & bug fixing | 2 | 2022-09-23 | 2022-09-26 | Done
18. Admin can import/export form data
|  | UI implementation | 4 | 2022-09-14 | 2022-09-21 | Done
|  | API implemntation | 4 | 2022-09-14 | 2022-09-21 | Done
|  | Test & bug fixing | 3 | 2022-09-23 | 2022-09-26 | Done
| Update Specification |  |  | 2022-09-19 | 2022-09-23 | Done
19: Merge code back-end vào code back-end của SmartOCR
|  | Update DB schema | 2 | 2022-09-27 | 2022-09-28 | To Do
|  | Migration Sequelize to SQL raw | 4 | 2022-09-27 | 2022-09-30 | To Do
|  | Add view engine hbs to system | 1 | 2022-09-29 | 2022-09-29 | To Do
|  | Module: Form (Update logic) | 8 | 2022-09-30 | 2022-10-11 | To Do
|  | Module: Web form (Create new) | 5 | 2022-10-03 | 2022-10-07 | To Do
|  | Testing & bug fixing | 5 | 2022-10-11 | 2022-10-17 | To Do